## Documentation
| Category | Requested By | File(s) | Status | Notes
Investor Onboarding Slides | Investor | Richard, July 1 11:22 PM | AI_Trading_Investor_Deck_Complete_14_Slides.pptx | ✅ Complete | Final version uploaded
Blockchain Gateway + NIDR Design | Security/IP | Richard, July 1 10:46 PM | Draft in progress (HDLL notes pending) | 🚧 In Dev | Needs patent claim summary
Profit Allocation Engine Spec | Yield Pools | Richard, July 1 10:34 PM | Draft in progress | ✳️ Queued | Align with tiered pool logic
📋 Manus Sprint Task Cards | Engineering | Richard, July 1 4:13 PM | 📋_Manus_Sprint_Task_Cards_-_July_1st_Update.pdf | ✅ Sent | Used for current sprint

## Code Drops
Code Module | Drop Date | File Name | Status | Next Action
MetaTrader Integration | June 28 | metatrader-complete-code-drop.zip | ✅ Production Ready | Deploy test instance
AI Onboarding Wizard | July 1 | ai-onboarding-wizard-complete-handoff-package.tar.gz | ✅ 100% Complete | Integrate with full dashboard
Strategy Builder Backend | June 25 | strategy_builder_backend_v1.zip | ✅ Integrated | Begin model training
Trading Dashboard UI | June 24 | trading_dashboard_ui_build.zip | ✅ Deployed to test env | Refine UI for investor demo

## Timeline Tracker
Milestone | Target Date | Current Status | Owner | Dependencies
Complete Onboarding Wizard | July 1 | ✅ Done | Richard | API Integration, UX Testing
Investor Slide Deck Finalization | July 2 | ⚙️ Final edits | Richard | Final investor feedback
Beta Test Deployment | July 4 | 🟡 Preparing environment | Manus | All backend modules stable
Begin AI Model Training | July 5 | 🔜 Scheduled | AI Team | Training dataset verification